## Slide 1: Second Rural Development Program (RDP2) Solomon Islands
Speakers
Michael Ho’ota
Mark Johnston

## Slide 2: Project Background
February 2015 – February 2020
US$46.9 million
Implementing agency: Ministry of Development Planning and Aid Coordination & Ministry of Agriculture and Livestock
Project Objective: To improve basic infrastructure and services in rural areas and to strengthen the linkages between smallholder farming households and markets.
Geographical coverage & scope: Community Development Grants in all 172 rural wards in the country and 40+ Agribusiness Partnership Grants across the country.

## Slide 3: Design of Local Economic Development/ Livelihoods Component
Problems being solved -Lack of access to basic services (clean water, health education) and economic activities in rural communities (subsistence lifestyles)
Design based on background analyses - Agriculture and Rural Development Strategy (2007) Coconut and cocoa value chain analysis (2014), RDP phase 1 (2008-2015), PNG PPAP.
Interventions - Small scale community infrastructure and services, Agricultural partnerships, Equity facility
Profitability, commercial viability and sustainability - Community infrastructure operations and maintenance plan and partnership between agribusinesses and the value chain and farmers
Beneficiaries - 44,188 (22,190 women) have improved quality of, and/or, access to rural infrastructure or services and 6,695 households engaged in productive partnerships with commercial enterprises and 2,846 have received agriculture and livestock support to recover incomes lost from April 2014 flooding
Amount for Local Economic Development/Livelihoods - US$13.6 million Small scale community infrastructure and services, US$11.2 million agricultural partnerships, equity facility

## Slide 4: Challenges and Lessons Learned
Difficulties and solutions
Infrastructure and services
Community participation coordination - increase program engagement with the communities, better transparency information awareness.
Large number of water sub-projects and lack of engineers to design them – recruited and train graduates
A new community each funding cycle – provide increased support to the implementation committee at all stages of implementation
Changing mindsets – consultations and awareness
Agricultural partnerships
Smallholder farmers do farming when they need money and don’t see it as a business – training and awareness on basic business and financial literacy, farm management and planning.
Lack of financial services for farmers - savings clubs, link with SINPF youSave program
Lack of loyalty of farmers and co-partners to the agribusiness lead partner – try to make it beneficial to all partners along the value chain
Geographical difficulty of numerous small islands, transport costs and logistics – promote value adding in the rural communities, and higher value products, eg coconut oil VCO and solar dried cocoa
Impediments in scaling up the project to reach more beneficiaries
Infrastructure and services – resources, financial and human
Limited number of agribusinesses, capacity of agribusinesses
Economics of enterprises in the more isolated islands, lack of infrastructure (roads, wharfs, shipping etc)
Farmers access to finance

## Slide 5: Results
Infrastructure and services
214 sub-projects one in every ward plus 40 disaster recovery
129 Health, 37 Housing and Community, 37 Education, 11 Economic Affairs
82 sub-projects completed
Agriculture Partnerships
Improved service delivery to partnership farmers
Improved linkages along the value chain (farmers to markets)
Improved quality of cocoa and price & production techniques improved
More value adding coconut to oil in the villages replacing copra
Commercializing indigenous nuts – diversifying rural incomes

## Slide 6: Lessons Learned
Advice on design, implementation and what to do differently
Infrastructure and services - Each community have access to ongoing annual funding to enable better community development, getting one sub-project if lucky isn’t enough, no long-term planning, can limit the type of infrastructure selected, communities don’t benefit from the lessons learnt.
Promote economic community infrastructure.
Agriculture partnerships – to date only relatively small number of farmers being assisted, need to upscale, agribusinesses need more capacity to do so and more resources.
Look at a micro-credit system for smallholder farmers and traders in the value chain.