## Slide 1: Action Planning 30/60/90:
30 DAYS
60 DAYS
90 DAYS
Actions/Activities:
Actions/Activities:
Actions/Activities:
Focus areas – pick 3/4:
Developing a sense of community
Securing resources (funding/human)
Strengthening Core group/core team
Developing a CoP Strategy
Responding to member needs
Securing leadership support
Onboarding new members
Developing indicators of success for your CoP
Celebrating CoP successes
Other:
How will you measure success? SMART Indicators:
This document is part of a CoP Toolkit to help you develop impactful Communities of Practice in the development sector. Access the full CoP Toolkit.

## Slide 2: Action Planning 30/60/90:
Actions/Activities:
Responsible – By whom:
Desired Outcomes
Timeframe – By when:
Resources:
30 days
60 days
90 days
This document is part of a CoP Toolkit to help you develop impactful Communities of Practice in the development sector. Access the full CoP Toolkit.

## Slide 3: Action Planning: 30/60/90 - Example
30 DAYS
60 DAYS
90 DAYS
Focus areas – pick 3/4:
Developing a sense of community
Securing resources (funding/human)
Strengthening Core group/core team
Developing a CoP Strategy
Responding to member needs
Securing leadership support
Onboarding new members
Developing indicators of success for your CoP
Celebrating CoP successes
Other:
Actions/Activities
Sense of community
Organize an informal speed networking event
Strengthening Core Team
Set up a weekly/bi-weekly meeting
Clarify roles and responsibilities
Recruit one volunteer
Developing a CoP Strategy
Organize the results from member interviews
Develop and launch an online survey of members
Onboarding new members
Set up an online platform
Basic training for new members
Target first wave (25 people)
Actions/Activities
Sense of community
Follow up to the networking event with stories from the members (newsletter)
Strengthening Core Team
Recruit one volunteer
Organize an informal lunch/happy hour for team building
Developing a CoP Strategy
Analyze the results from the online survey
Prepare a draft strategy
Validate the draft strategy with core team
Responding to new member needs
Offering time bounded e-discussion (based on member feedback
Plan a monthly roundtable
Add additional content on the main topic
Actions/Activities
Sense of community
Organize another networking event for CoP
Strengthening Core Team
Recognize core team members with their management
Developing a CoP Strategy
Validate the strategy with the CoP
Validate the strategy with management
Onboarding new members
Reach out to first 25 and check in (what's working and what's not)
Onboard new wave (25 people)
Understand old/new member needs
This document is part of a CoP Toolkit to help you develop impactful Communities of Practice in the development sector. Access the full CoP Toolkit.